## Slide 1
CapEx Master Data Governance
Council Kickoff
Meeting date: [TBD] | Audience: CapEx committee, domain owners, data stewards
Source: control-governance / architecture / capex-master-data-management-framework.md
CAPEX COMMITTEE BRIEFING
Purpose: Ratify CapEx MDM framework, confirm ownership, approve Phase 0–1 mobilization

## Slide 2
Cross-domain master data breaks at handoffs — not inside Oracle modules
EXECUTIVE TAKEAWAY
Controls exist, continuity doesn't — Domain CapEx controls already operate in Procurement, Projects, AP, and Fixed Assets; the gap is identifier continuity across boundaries.
Fix the chain before new tooling — Five global identifiers (CapExInvestmentID, ProjectNumber, GlobalAssetTag, SupplierPartyNumber, LocationCode) and ten enterprise DQ rules (MDQ-01–10).
Highest near-term value — L4→L5 investment-to-project linkage and MDQ-01/02 enforcement at requisition.

## Slide 3
Approve framework, name the chair, and fund Phase 0–1 only
DECISION REQUESTS
# | Decision | Options | Recommended
D1 | Adopt CapEx MDM framework | Approve / Revise / Defer | Approve MDM-1–10
D2 | Name MDM Council chair | Finance / PMO nominee | CapEx process owner
D3 | Ratify identifier policy | Approve / Workshop formats | Approve; workshop in Phase 1
D4 | Upstream pattern L1–L4 | A: EPM · B: PPM · C: Intake | Time-box to Phase 1
D5 | Fund mobilization | Yes / No / Partial | Yes — weeks 1–10 only

## Slide 4
Metrics are defined — baseline and enforce are the gaps
KPI AND CONTROL HEALTH
KPI / control | Target | Current | Status
CXM-01 Reqs w/ valid project + category | ≥ 95% | Not baselined | Phase 0
CXM-03 CIP aging > 90 days | < 10% | Not baselined | Phase 0
CXM-05 FA–GL recon exceptions | 0 material | Not baselined | Per close
MDQ-01 Valid ProjectNumber + task | 100% | Not enforced | Phase 2
MDQ-10 Investment ID traceable | 100% | Not enforced | Phase 1
Handoff SLA H-01–H-06 | ≥ 90% | Not measured | CXM-07

## Slide 5
Seven open risks — three are high severity at capitalization and authorization
TOP RISKS AND ISSUE STATUS
Risk / issue | Sev | Owner | Status | ETA
Investment ID not on project (L4→L5) | High | CapEx owner | Open | Wk 10
Duplicate asset cap (MDQ-09) | High | Asset Acct Mgr | Manual only | Wk 20
Opex on CapEx req (MDQ-02) | High | Controllership | Not blocked | Wk 16
Duplicate / unqualified supplier | Med | Supplier MDM | Partial | Wk 18
CIP not cleared after PIS | Med | Asset Accountant | Open | Wk 28
Upstream pattern undecided | Med | CFO delegate | Open | Wk 8
CapEx funnel distrusted | Med | Controllership | No lineage | Wk 28

## Slide 6
Boundary master data fails — not in-domain quality
ROOT-CAUSE THEMES
No golden keys — H-01–H-06 fail when CapExInvestmentID, ProjectNumber, or GlobalAssetTag break.
Strong domain MD, weak boundary MD — enterprise MDQ-01–10 not operational across handoffs.
Process gates without data contracts — overlay SLAs exist; required fields and MDQ enforcement do not.
Upstream portfolio disconnected — L1–L4 in EPM/PPM/spreadsheet without L4→L5 cross-reference.
Detection after the fact — post-hoc audit instead of a system block at requisition (MDQ-01/02).

## Slide 7
Stewards before automation — a 28-week remediation plan
REMEDIATION PLAN
Action | Owner | Start | End | Dependency
Ratify MDM + identifier policy | CapEx owner | Wk 1 | Wk 1 | D1, D3 approval
Charter MDM Council + Steward WG | Ent. data architect | Wk 1 | Wk 2 | Named chair (D2)
Baseline MDQ-01/02 (top 3 categories) | P2P + Control | Wk 2 | Wk 4 | Audit access
Select upstream pattern A/B/C | Portfolio Forum | Wk 5 | Wk 8 | D4 selection
Publish Investment ID ↔ Project cross-ref | Portfolio steward | Wk 6 | Wk 10 | Pattern selected
Enforce MDQ-01/02 at requisition | IT ERP + Proc | Wk 11 | Wk 16 | Steward WG active
MDQ-09 at FA mass additions | Asset Accountant | Wk 14 | Wk 20 | FA queue SOP
CapEx funnel + MD quality dashboard | Control + BI | Wk 21 | Wk 28 | Lineage template
Monthly MDM Council + MD health scorecard | CapEx owner | Wk 5 | Ongoing | Council charter

## Slide 8
Name the chair today and fund weeks 1–10 mobilization
OPEN DECISIONS AND MILESTONES
Name the CapEx process owner / MDM Council chair.
Confirm stewards — portfolio, project, supplier MDM, asset, GL.
Limit Phase 0–1 to the top 3 asset categories.
OPEN DECISIONS
MILESTONES
Wk 4 — Baseline audit: MDQ-01/02 pass rate published.
Wk 8 — Upstream pattern A/B/C selected.
Wk 10 — L4→L5 cross-reference live; MDQ-10 pilot.
Wk 16 — MDQ-01/02 system enforcement on pilot categories.
Wk 28 — Certified CapEx funnel dashboard with MD-quality overlay.

## Slide 9
Appendix — Governed terms
DEFINITIONS
Term | Definition
CapExInvestmentID | Enterprise ID from intake through retirement
ProjectNumber | Oracle authoritative project ID
GlobalAssetTag | Unique physical asset ID in FA register
CIP | Costs accumulated before place in service
PIS | Depreciation start trigger
MDQ-01–10 | Enterprise cross-domain data-quality rules

## Slide 10
Appendix — Twelve-stage CapEx lifecycle
L1–L4 UPSTREAM · L5–L12 MAPS TO OVERLAY S1–S6
Platform: Oracle Fusion Cloud 26B · optional EPM / external PPM for L1–L4
Maturity: Foundational → Defined (12-month horizon)
Framework status: v1.0 Draft — tenant segment values TBD
PLAN · L1–L4
L1 Strategy › L2 Demand › L3 Feasibility › L4 Authorization
BUILD · L5–L8
L5 Budgeting › L6 Design › L7 Sourcing › L8 Construction
REALIZE · L9–L12
L9 Capitalization › L10 Commissioning › L11 Op. handoff › L12 Retirement
SIX DATA DOMAINS
Investment & Portfolio · Project & WBS · Financial Coding · Supplier & Contract · Location & Site · Asset Register

## Slide 11
Appendix — Supporting evidence
REPOSITORY REFERENCES
Architecture
architecture/capex-master-data-management-framework.md
architecture/capex-lifecycle-governance-overlay.md
Oracle Fusion 26B — Governed Data & Analytics
packages/oracle-fusion-procurement-26b/02-governed-data-and-analytics.md
packages/oracle-fusion-project-management-26b/02-governed-data-and-analytics.md
packages/oracle-fusion-ap-i2p-26b/02-governed-data-and-analytics.md
packages/oracle-fusion-fixed-assets-26b/02-governed-data-and-analytics.md
packages/oracle-fusion-general-ledger-26b/02-governed-data-and-analytics.md